## Slide 1: MAVEN BUILDER TRAINING FORCE ROLLOUT PLAN
UNCLASSIFIED
UNCLASSIFIED
UNCLASSIFIED
USAREUR-AF Operational Data Team | C2DAO | MAR 2026

## Slide 2
MAVEN BUILDER TRAINING — FORCE ROLLOUT PLAN
UNCLASSIFIED
PHASE | ACTION | DECISION / OWNER | SUCCESS STANDARD
1 ¦ COMMAND AUTHORITY | Issue training directive (EXORD or policy memo) designating Maven Builder Training as a command priority. | CDR decision: mandatory vs. encouraged by role. G3/J3 staff action. | Signed directive published to all subordinate units.
2 ¦ CADRE STANDUP | Identify and assign 5 cadre: 1 OIC + 4 SMEs covering TM-10/20/30/40 tracks. Develop instructor SOP. | G6/G2/S6 nominations. OIC appointed by CDR. | Cadre certified; SOP signed; instructors completed TM-40 series.
3 ¦ AUDIENCE SEQUENCING | Phase training: TM-10 (all staff) → TM-20/30 (data-adjacent billets) → TM-40 series by role. | G3 decision: phased by echelon or MOS priority. Unit S3s build into ATP. | 100% TM-10 completion; TM-40 track assignments published.
4 ¦ RESOURCE & ACCESS | Provision Foundry seats, schedule lab time/VTC blocks, integrate into unit training calendar. | G6 action: license provisioning. G3: calendar deconfliction. | All students have Foundry access NLT training start date.
5 ¦ TRACK & REPORT | Establish completion tracking in DTMS/ATRRS. Set Go/No-Go checkpoints per MTP. Report monthly. | G1/S1 action: reporting format. CDR sets completion deadline (recommended D+180). | Monthly completion report to CDR; Go/No-Go recorded per student.
6 ¦ FEEDBACK & SUSTAIN | Conduct AAR after first cohort; update curriculum and cadre SOP quarterly. Integrate into onboarding. | Cadre OIC owns curriculum updates. CDR approves policy changes. | Quarterly AAR complete; curriculum version controlled; onboarding updated.
RECOMMENDED TIMELINE: Directive signed NLT D+30 | Cadre designated NLT D+45 | First TM-10 cohort NLT D+60 | Full TM-40 coverage NLT D+180
USAREUR-AF · C2DAO · MSS-POI-001 · MAR 2026 · UNCLASSIFIED